## Sheet1
Rama | Sprint Details | Tasks
| Sprint 1 | What task did I work on/complete? | design of UI Wireframes, Updating Sprint Journal, Update of Weekly scrum report
|  | What am I planning to do to next? | Complete UI Wireframes and start the Front End Development
|  | What tasks are blocked waiting on another team member? | None
| Sprint 2 | What task did I work on/complete? | Completed UI Wireframes and started the Front End Development for the application also Updated Weekly scrum report
|  | What am I planning to do to next? | Started user interface for Landing screen, Login and Register Page
|  | What tasks are blocked waiting on another team member? | None
| Sprint 3 | What task did I work on/complete? | Implemented UI for the Landing, Login and Register page, Update Weekly scrum report
|  | What am I planning to do to next? | Backend of Integrate Login and Register page
|  | What tasks are blocked waiting on another team member? | None
| Sprint 4 | What task did I work on/complete? | Completed integrating login and register page with the backend and update weekly scrum report
|  | What am I planning to do to next? | Implement and integrate search hotel functionality based on location for particular dates
|  | What tasks are blocked waiting on another team member? | None
| Sprint 5 | What task did I work on/complete? | Completed search functionality with backend integration and testing all the features implemented and updated weekly srum report
|  | What am I planning to do to next? | Implementing add room functionality for the hotel employee
|  | What tasks are blocked waiting on another team member? | None
| Sprint 6 | What task did I work on/complete? | Completed add room with backend integration and updated weekly srum report
|  | What am I planning to do to next? | Implementing view hotel description in frontend for users and listing all the bookings in admin module and testing
|  | What tasks are blocked waiting on another team member? | Implementing booking history in backend
| Sprint 7 | What task did I work on/complete? | Completed view hotel description and listing all the bookings in admin module, Fixing few endpoints in backend
|  | What am I planning to do to next? | Testig the application flow and fixing bugs
|  | What tasks are blocked waiting on another team member? | None
Harsha | Sprint Details | Tasks
| Sprint 1 | What task did I work on/complete? | design of UI Wireframes, Updating Sprint Journal, Update of Weekly scrum report
|  | What am I planning to do to next? | Complete UI Wireframes and start the Front End Development
|  | What tasks are blocked waiting on another team member? | None
| Sprint 2 | What task did I work on/complete? | Completed UI Wireframes and started the Front End Development for the application, Update Weekly scrum report
|  | What am I planning to do to next? | worked on UI Pages Admin Add Room, Admin All Booking Screens, Admin Upper Bar
|  | What tasks are blocked waiting on another team member? | None
| Sprint 3 | What task did I work on/complete? | Finished building UI Pages Admin Add Room, Admin All Booking Screens, Admin Upper Bar
|  | What am I planning to do to next? | Work on Admin User Screens, Profile Screen
|  | What tasks are blocked waiting on another team member? | None
| Sprint 4 | What task did I work on/complete? | worked on Admin User Screens, Profile Screen
|  | What am I planning to do to next? | Integrate Admin Add Room, Admin All Booking Screens, Admin Upper Bar
|  | What tasks are blocked waiting on another team member? | None
| Sprint 5 | What task did I work on/complete? | Integrated Admin Add Room, Admin All Booking Screens, Admin Upper Bar,Admin User Screens, Profile Screen
|  | What am I planning to do to next? | Work on editbooking screen
|  | What tasks are blocked waiting on another team member? | None
| Sprint 6 | What task did I work on/complete? | Worked on editbooking page
|  | What am I planning to do to next? | Testing the application flow and fixing bugs.
|  | What tasks are blocked waiting on another team member? | None
| Sprint 7 | What task did I work on/complete? | Fixed Edit boooking page, Update prices page, developed an endpoint for update prices.
|  | What am I planning to do to next? | Testing the application flow, deploying and fixing bugs
|  | What tasks are blocked waiting on another team member? | None
Aravind | Sprint Details | Tasks
| Sprint 1 | What task did I work on/complete? | Worked on designing of UI Wireframes, Update Weekly scrum report
|  | What am I planning to do to next? | Revise the UI Wireframes and start the Frontend Components
|  | What tasks are blocked waiting on another team member? | None
| Sprint 2 | What task did I work on/complete? | Completed drawing UI Wireframes, started working on UI componets, Updated Weekly scrum report
|  | What am I planning to do to next? | Work on Footer, Hotel image display, Image sliders
|  | What tasks are blocked waiting on another team member? | None
| Sprint 3 | What task did I work on/complete? | Completed the UI for Booking page, Image sliders and Updated Weekly scrum report
|  | What am I planning to do to next? | Include checkbox Amentinies,update Payment details accordingly on booking page
|  | What tasks are blocked waiting on another team member? | None
| Sprint 4 | What task did I work on/complete? | Added Amenites, Hotel room and rewards details on booking page, Updated Weekly scrum report
|  | What am I planning to do to next? | Hotel detail page and Booking history pages
|  | What tasks are blocked waiting on another team member? | None
| Sprint 5 | What task did I work on/complete? | Integrated Hotel detail page with other components on frontend, Updated Weekly scrum report
|  | What am I planning to do to next? | Work on diagrams, and Booking history page
|  | What tasks are blocked waiting on another team member? | None
| Sprint 6 | What task did I work on/complete? | Worked on booking history page integration, Rewards integration into booking page and testing completed.
|  | What am I planning to do to next? | Work on all diagrams and start documentation.
|  | What tasks are blocked waiting on another team member? | None
| Sprint 7 | What task did I work on/complete? | Completed Architecture, Usecase, Deployment and component diagrams,
|  | What am I planning to do to next? | Fix if any bugs/ issues/styling
|  | What tasks are blocked waiting on another team member? | None
Jayanth | Sprint Details | Tasks
| Sprint 1 | What task did I work on/complete? | Adding backend Index file, setting up the users routing, adding user service file and integrate validation
|  | What am I planning to do to next? | User models and jwt service file
|  | What tasks are blocked waiting on another team member? | None
| Sprint 2 | What task did I work on/complete? | Adding auth routes and service changes, adding jwt service file and auth middleware. adding user models changes
|  | What am I planning to do to next? | Fixes in model files and routes
|  | What tasks are blocked waiting on another team member? | None
| Sprint 3 | What task did I work on/complete? | minor changes in model files,adding hotel controller and servic files, adding hotel routes, add rooms db migration
|  | What am I planning to do to next? | Add amenities and modify the price based on amenities.
|  | What tasks are blocked waiting on another team member? | None
| Sprint 4 | What task did I work on/complete? | adding rooms route, controller and service changes, introducing amenities and integrating with rooms table, add hotel and room relationship, add peak price model, add bookings db table
|  | What am I planning to do to next? | Fixing book functionality
|  | What tasks are blocked waiting on another team member? | None
| Sprint 5 | What task did I work on/complete? | add booking functionality - temp, Update room service, Add booking roots
|  | What am I planning to do to next? | Add loyality points and calculate rewards
|  | What tasks are blocked waiting on another team member? | None
| Sprint 6 | What task did I work on/complete? | Add loyality points based pricing, Derive loyalty points from booking
|  | What am I planning to do to next? | Calculate price based on number of guests.
|  | What tasks are blocked waiting on another team member? | None
| Sprint 7 | What task did I work on/complete? | Calculating Price based on number of guests, Dynamic filter, add guest info on booking
|  | What am I planning to do to next? | Login Validations, Dynamic pricing, Adding 7 days limts for booking.
|  | What tasks are blocked waiting on another team member? | None